## Roster
Employee ID | First Name | Last Name | Personal Email | Company Email | Phone | Location | Timezone | Job Title | Department | Team | Manager | Employment Type | Start Date | Onboarding Buddy | Notes | Cohort | Welcome Email Sent | Slack Announcement Sent | Calendar Invite Sent
EMP-001 | Jane | Doe | jane.doe@gmail.com | jane.doe@company.com | +1-555-101-0001 | Austin, TX | CT (UTC-6) | Senior Backend Engineer | Engineering | Platform | Sarah Johnson | Full-Time | 2026-04-13 | Alex Smith |  | Cohort 1
EMP-002 | Marcus | Lee | marcus.lee@gmail.com | marcus.lee@company.com | +1-555-101-0002 | Brooklyn, NY | ET (UTC-5) | Software Engineer II | Engineering | Frontend | Sarah Johnson | Full-Time | 2026-04-13 | Priya Nair |  | Cohort 1
EMP-003 | Aisha | Okafor | aisha.okafor@gmail.com | aisha.okafor@company.com | +44-7700-900003 | London, UK | GMT (UTC+1) | Staff Engineer | Engineering | Infrastructure | David Kim | Full-Time | 2026-04-20 | Tom Rivera |  | Cohort 2
EMP-004 | Carlos | Mendez | carlos.mendez@gmail.com | carlos.mendez@company.com | +1-555-101-0004 | Denver, CO | MT (UTC-7) | Junior Software Engineer | Engineering | Platform | Sarah Johnson | Full-Time | 2026-04-20 | Alex Smith | New grad hire | Cohort 2
EMP-005 | Priya | Nair | priya.nair@gmail.com | priya.nair@company.com | +1-555-101-0005 | San Francisco, CA | PT (UTC-8) | Senior Software Engineer | Engineering | Data | David Kim | Full-Time | 2026-04-27 | Marcus Lee |  | Cohort 3
EMP-006 | Tom | Rivera | tom.rivera@gmail.com | tom.rivera@company.com | +1-555-101-0006 | Miami, FL | ET (UTC-5) | DevOps Engineer | Engineering | Infrastructure | David Kim | Full-Time | 2026-04-27 | Jane Doe |  | Cohort 3
EMP-007 | Yuki | Tanaka | yuki.tanaka@gmail.com | yuki.tanaka@company.com | +81-90-0000-0007 | Tokyo, Japan | JST (UTC+9) | Software Engineer II | Engineering | Platform | Sarah Johnson | Contract | 2026-05-04 | Aisha Okafor | Contract — 6 months | Cohort 4
EMP-008 | Fatima | Al-Hassan | fatima.alhassan@gmail.com | fatima.alhassan@company.com | +971-50-000-0008 | Dubai, UAE | GST (UTC+4) | Senior Backend Engineer | Engineering | Data | David Kim | Full-Time | 2026-05-04 | Carlos Mendez |  | Cohort 4
EMP-009 | Liam | O'Brien | liam.obrien@gmail.com | liam.obrien@company.com | +353-87-000-0009 | Dublin, Ireland | IST (UTC+1) | Software Engineer I | Engineering | Frontend | Sarah Johnson | Full-Time | 2026-05-11 | Tom Rivera |  | Cohort 5
EMP-010 | Zara | Ahmed | zara.ahmed@gmail.com | zara.ahmed@company.com | +1-555-101-0010 | Chicago, IL | CT (UTC-6) | Engineering Manager | Engineering | Platform | Sarah Johnson | Full-Time | 2026-05-11 | Priya Nair | Transitioning from IC | Cohort 5

## Checklist Tracker
Employee ID | Name | Start Date | Cohort | Pre-Day 1 Complete | Day 1: Orientation | Day 1: Tools Access | Day 1: Dev Setup | Day 2: Architecture | Day 2: First PR Merged | Day 3: Product Overview | Day 3: Security Training | Day 4: Sprint Ceremonies | Day 4: First Ticket | Day 5: Week 1 Retro | Day 5: All-Hands Intro | Security Quiz Done | All Tools Working | Overall Status
EMP-001 | Jane Doe | 2026-04-13 | Cohort 1 | [14 empty] | Not Started
EMP-002 | Marcus Lee | 2026-04-13 | Cohort 1 | [14 empty] | Not Started
EMP-003 | Aisha Okafor | 2026-04-20 | Cohort 2 | [14 empty] | Not Started
EMP-004 | Carlos Mendez | 2026-04-20 | Cohort 2 | [14 empty] | Not Started
EMP-005 | Priya Nair | 2026-04-27 | Cohort 3 | [14 empty] | Not Started
EMP-006 | Tom Rivera | 2026-04-27 | Cohort 3 | [14 empty] | Not Started
EMP-007 | Yuki Tanaka | 2026-05-04 | Cohort 4 | [14 empty] | Not Started
EMP-008 | Fatima Al-Hassan | 2026-05-04 | Cohort 4 | [14 empty] | Not Started
EMP-009 | Liam O'Brien | 2026-05-11 | Cohort 5 | [14 empty] | Not Started
EMP-010 | Zara Ahmed | 2026-05-11 | Cohort 5 | [14 empty] | Not Started

## Key Dates & Actions
Date | Day | Cohort | Action Item | Hires Involved | Owner | Status
2026-04-08 | Wed | Cohort 1 | Send welcome emails + calendar invites | Jane Doe, Marcus Lee | People Ops / Sarah Johnson | Pending
2026-04-09 | Thu | Cohort 1 | Post pre-arrival Slack announcement (#engineering) | Jane Doe, Marcus Lee | Sarah Johnson | Pending
2026-04-10 | Fri | Cohort 1 | Confirm equipment delivery for Cohort 1 | Jane Doe, Marcus Lee | IT | Pending
2026-04-13 | Mon | Cohort 1 | Day 1 — Orientation, Dev Setup, Team Lunch, Tools Walkthrough | Jane Doe, Marcus Lee | Sarah Johnson / Buddies | Pending
2026-04-14 | Tue | Cohort 1 | Day 2 — Architecture Deep Dive, First PR | Jane Doe, Marcus Lee | Sarah Johnson / Buddies | Pending
2026-04-15 | Wed | Cohort 1 | Day 3 — Product & Roadmap, Security Training | Jane Doe, Marcus Lee | Cross-functional | Pending
2026-04-15 | Wed | Cohort 2 | Send welcome emails + calendar invites | Aisha Okafor, Carlos Mendez | People Ops / Sarah Johnson & David Kim | Pending
2026-04-16 | Thu | Cohort 1 | Day 4 — Sprint Ceremonies, First Ticket | Jane Doe, Marcus Lee | Sarah Johnson / Buddies | Pending
2026-04-16 | Thu | Cohort 2 | Post pre-arrival Slack announcement (#engineering) | Aisha Okafor, Carlos Mendez | Sarah Johnson / David Kim | Pending
2026-04-17 | Fri | Cohort 1 | Day 5 — Week 1 Retro, All-Hands, End-of-Week wrap-up Slack | Jane Doe, Marcus Lee | Sarah Johnson | Pending
2026-04-17 | Fri | Cohort 2 | Confirm equipment delivery for Cohort 2 | Aisha Okafor, Carlos Mendez | IT | Pending
2026-04-20 | Mon | Cohort 2 | Day 1 — Orientation, Dev Setup, Team Lunch, Tools Walkthrough | Aisha Okafor, Carlos Mendez | David Kim & Sarah Johnson / Buddies | Pending
2026-04-21 | Tue | Cohort 2 | Day 2 — Architecture Deep Dive, First PR | Aisha Okafor, Carlos Mendez | Managers / Buddies | Pending
2026-04-22 | Wed | Cohort 2 | Day 3 — Product & Roadmap, Security Training | Aisha Okafor, Carlos Mendez | Cross-functional | Pending
2026-04-22 | Wed | Cohort 3 | Send welcome emails + calendar invites | Priya Nair, Tom Rivera | People Ops / David Kim | Pending
2026-04-23 | Thu | Cohort 2 | Day 4 — Sprint Ceremonies, First Ticket | Aisha Okafor, Carlos Mendez | Managers / Buddies | Pending
2026-04-23 | Thu | Cohort 3 | Post pre-arrival Slack announcement (#engineering) | Priya Nair, Tom Rivera | David Kim | Pending
2026-04-24 | Fri | Cohort 2 | Day 5 — Week 1 Retro, All-Hands, End-of-Week wrap-up Slack | Aisha Okafor, Carlos Mendez | David Kim & Sarah Johnson | Pending
2026-04-24 | Fri | Cohort 3 | Confirm equipment delivery for Cohort 3 | Priya Nair, Tom Rivera | IT | Pending
2026-04-27 | Mon | Cohort 3 | Day 1 — Orientation, Dev Setup, Team Lunch, Tools Walkthrough | Priya Nair, Tom Rivera | David Kim / Buddies | Pending
2026-04-28 | Tue | Cohort 3 | Day 2 — Architecture Deep Dive, First PR | Priya Nair, Tom Rivera | Managers / Buddies | Pending
2026-04-29 | Wed | Cohort 3 | Day 3 — Product & Roadmap, Security Training | Priya Nair, Tom Rivera | Cross-functional | Pending
2026-04-29 | Wed | Cohort 4 | Send welcome emails + calendar invites | Yuki Tanaka, Fatima Al-Hassan | People Ops / Sarah Johnson & David Kim | Pending
2026-04-30 | Thu | Cohort 3 | Day 4 — Sprint Ceremonies, First Ticket | Priya Nair, Tom Rivera | Managers / Buddies | Pending
2026-04-30 | Thu | Cohort 4 | Post pre-arrival Slack announcement (#engineering) | Yuki Tanaka, Fatima Al-Hassan | Sarah Johnson / David Kim | Pending
2026-05-01 | Fri | Cohort 3 | Day 5 — Week 1 Retro, All-Hands, End-of-Week wrap-up Slack | Priya Nair, Tom Rivera | David Kim | Pending
2026-05-01 | Fri | Cohort 4 | Confirm equipment delivery for Cohort 4 (intl shipping for Tokyo, Dubai) | Yuki Tanaka, Fatima Al-Hassan | IT | Pending
2026-05-04 | Mon | Cohort 4 | Day 1 — Orientation, Dev Setup, Team Lunch, Tools Walkthrough | Yuki Tanaka, Fatima Al-Hassan | Sarah Johnson & David Kim / Buddies | Pending
2026-05-05 | Tue | Cohort 4 | Day 2 — Architecture Deep Dive, First PR | Yuki Tanaka, Fatima Al-Hassan | Managers / Buddies | Pending
2026-05-06 | Wed | Cohort 4 | Day 3 — Product & Roadmap, Security Training | Yuki Tanaka, Fatima Al-Hassan | Cross-functional | Pending
2026-05-06 | Wed | Cohort 5 | Send welcome emails + calendar invites | Liam O'Brien, Zara Ahmed | People Ops / Sarah Johnson | Pending
2026-05-07 | Thu | Cohort 4 | Day 4 — Sprint Ceremonies, First Ticket | Yuki Tanaka, Fatima Al-Hassan | Managers / Buddies | Pending
2026-05-07 | Thu | Cohort 5 | Post pre-arrival Slack announcement (#engineering) | Liam O'Brien, Zara Ahmed | Sarah Johnson | Pending
2026-05-08 | Fri | Cohort 4 | Day 5 — Week 1 Retro, All-Hands, End-of-Week wrap-up Slack | Yuki Tanaka, Fatima Al-Hassan | Sarah Johnson & David Kim | Pending
2026-05-08 | Fri | Cohort 5 | Confirm equipment delivery for Cohort 5 (intl shipping for Dublin) | Liam O'Brien, Zara Ahmed | IT | Pending
2026-05-11 | Mon | Cohort 5 | Day 1 — Orientation, Dev Setup, Team Lunch, Tools Walkthrough | Liam O'Brien, Zara Ahmed | Sarah Johnson / Buddies | Pending
2026-05-12 | Tue | Cohort 5 | Day 2 — Architecture Deep Dive, First PR | Liam O'Brien, Zara Ahmed | Managers / Buddies | Pending
2026-05-13 | Wed | Cohort 5 | Day 3 — Product & Roadmap, Security Training | Liam O'Brien, Zara Ahmed | Cross-functional | Pending
2026-05-14 | Thu | Cohort 5 | Day 4 — Sprint Ceremonies, First Ticket | Liam O'Brien, Zara Ahmed | Managers / Buddies | Pending
2026-05-15 | Fri | Cohort 5 | Day 5 — Week 1 Retro, All-Hands, End-of-Week wrap-up Slack | Liam O'Brien, Zara Ahmed | Sarah Johnson | Pending

## Flags & Notes
# | Category | Description | Action Required | Owner | Priority
1 | Buddy Dependency | Priya Nair (Cohort 3, Apr 27) is assigned Marcus Lee (Cohort 1, Apr 13) as buddy. Marcus will only have 2 weeks of tenure by then. | Confirm Marcus is ready and willing to buddy after only 2 weeks on the job. | Sarah Johnson | Medium
2 | Buddy Dependency | Tom Rivera (Cohort 3, Apr 27) is assigned Jane Doe (Cohort 1, Apr 13) as buddy. Jane will also only have 2 weeks of tenure. | Confirm Jane is ready to buddy; consider a backup buddy from existing staff. | Sarah Johnson | Medium
3 | Buddy Dependency | Fatima Al-Hassan (Cohort 4, May 4) is assigned Carlos Mendez (Cohort 2, Apr 20) as buddy. Carlos is a new grad hire himself with only 2 weeks of tenure. | Strongly consider reassigning Fatima's buddy to someone more senior on David Kim's team. | David Kim | High
4 | Contract Hire | Yuki Tanaka (EMP-007) is a 6-month contractor based in Tokyo. May need different access levels, compliance track, or equipment provisioning. | Verify contract-specific onboarding steps with Legal/HR. Confirm international equipment shipping timeline. | People Ops / Legal | High
5 | Role Transition | Zara Ahmed (EMP-010) is transitioning from IC to Engineering Manager. The standard IC-focused checklist (first PR, first ticket) may not apply. | Customize Zara's checklist: skip PR/ticket tasks; add manager-track items (1:1 setup with reports, leadership orientation, team context sessions). | Sarah Johnson | High
6 | Calendar / Timezone | The .ics calendar file is anchored to EDT (America/New_York, starting Apr 13). Hires in London (UTC+1), Tokyo (UTC+9), Dubai (UTC+4), and Dublin (UTC+1) need timezone-adjusted session times. | Generate per-cohort .ics files with times adjusted to each hire's local timezone, or confirm hires will attend in ET. | People Ops | Medium
7 | Template Gaps | Welcome email and Slack templates contain placeholders not present in the roster: PREVIOUS_COMPANY, BUDDY_ROLE, BUDDY_TENURE, IT_CONTACT_NAME, IT_CONTACT_EMAIL, HR_NAME, HR_EMAIL, COMPANY_NAME, ENG_LEAD. | Collect this missing data from HR/managers before sending any comms. See message bundle for fields marked [TO BE FILLED]. | People Ops | High